## Sheet1
Product Backlog
[12 empty] | making modification in 21/4/2018 |  |  |  |  | Sprint Backlog Table
For Sprint 1
[5 empty] | Assigned to Sprint | Story Points | Status | priority | Sprint Ready | Story | Task Name | Status Recurrently | Reamaininh hour recurrently |  | Status | Remaining Hours | Assigned To | Task Name | Estemated Hours |  | Item ID | Sprint
| Velocity Estimation |  |  |  | No | 24 | In Progress | High | No | No | Sprint1 (LoginPage) | Completed |  | 0 |  | 4 | Mohamed montaser | Create table of users in database | 4 | 4 | 1 | 1
[5 empty] | Yes | 12 | Complete | High | Yes | Yes | Task 1 (tables of the user regestration) | completed |  | 0 |  | 5 | ahmed mansour | encoding the passowrd in data base |  | 5 | 2 | 1 |  | Forecast Burns Down | Forecast Burns Down | Targed Burn Down(ideal progrees toward completion) | Work Day(Sprint 1)
[5 empty] | Yes | 8 | Complete | High | Yes | Yes | task2 (encoding the passowrd ) | Completed |  | 0 |  | 6 | Ester | Navigation to Home page |  | 6 | 3 | 1 |  | 69 | 69 | 69 | 1
[24 empty] | 55 | 57 | 59 | 2
Result | Completed | Commitments |  | Sprint | Yes | 4 | Complete | High | Yes | No | Task 3 (Design Login page) | Completed |  | 0 |  | 8 | ahmed mansour | stuff page coding and design |  | 8 | 4 | 2 |  | 50 | 45 | 49 | 3
[24 empty] | 43 | 39 | 40 | 4
35 | 24 |  | 24 | Sprint1 | Yes | 64 | In Progress | High | Yes | Yes | Sprint2(stuff page Fragmentations) | In Progress |  | 1 |  | 4 | mohamed montaser | knowing the attendance of employee |  | 4 | 5 | 2 |  | 42 | 30 | 35 | 5
[24 empty] | 45 | 20 | 25 | 6
| 48 |  | 64 | Sprint2 | Yes | 32 | complete | medium | Yes | Yes | Task4(knowing the attendance of employee ) | not completed |  | 4 |  | 4 | ahmed mansour | Employee approvals and Searching |  | 4 | 6 | 2 |  | 39 | 18 | 20 | 7
[24 empty] | 30 | 10 | 15 | 8
| 48 |  | 80 | Sprint3 | No | 16 | Not Started | Low | Yes | No | task5 (Employee approvals and Searching ) | Completed |  | 0 |  | 5 | ahmed mansour | Create admin and user previliges |  | 5 | 7 | 2 |  | 15 | 8 | 8 | 9
[24 empty] | 5 | -12 | 0 | 10
| 20 |  | 68 | Sprint 4 | yes | 5 | complete | Medium | Yes | Yes | task6 (knowing information ) | Completed |  | 0 |  | 6 | ahmed mansour | Knowing and edit informations |  | 6 | 8 | 2
[5 empty] | Yes | 11 | Complete | medium | Yes | Yes | task7(edit information) | Completed |  | 0 |  | 6 | mohamed khaled | Create Student form Design |  | 6 | 9 | 3
[5 empty] | Yes | 80 | In Progress | medium | No | Yes | Sprint 3(student Affairs Page) | In Progress |  | 3 |  | 7 | ahmed mansour | Search and make edit on students |  | 7 | 10 | 3
[5 empty] | No | 48 | Completed | Medium | Yes | Yes | Task8(Student form Design) | Completed |  | 0 |  | 5 | Dina ashraf | Student Enrollement Form Design |  | 5 | 11 | 4
[5 empty] | Yes | 16 | In Progress | Low | No | Yes | Task9(Search on Student) | In Progress |  | 4 |  | 4 | ahmed mansour | submit and send parameter |  | 4 | 12 | 4
Sprint Burn Down for Sprint 1
[5 empty] | Yes | 16 | In Progress | medium | Yes | Yes | Task10(Edit On Student) | Completed |  | 0 |  | 2 | Ester | connect with the student table |  | 2 | 13 | 4
[5 empty] | Yes | 68 | In Progress | medium | No | Yes | Sprint 4(StudentEnrollement page) | In Progress |  | 3 |  | 3 | ahmed mansour | Submit Function and button |  | 3 | 14 | 4
[5 empty] | Yes | 16 | completed | medium | No | No | Task11(Student Enrollement Form Design) |  |  | 15 |  | 69 |  |  |  | 69 | Total
[5 empty] | Yes | 32 | In Progress | High | No | no | Task12(submit and send parameter)
[5 empty] | No | 4 | Completed | Low | Yes | No | Task 13(connect with the student table)
[5 empty] | No | 16 | In Progress | High | No | Yes | Task 14(Submit Function and button)
[5 empty] | No | 96 | In Progress | Hight | No | Yes | Sprint5(kitchen Page)
Sprint's Information(Step 1)
|  |  |  | We used 80% as an indication of the the level productivity or utilization for development the tasks | [5 empty] | 2018-03-01 | Start Date
[10 empty] | 2018-04-08 | End Date
[10 empty] | 27 | Elapsed Days
[10 empty] | 0 | Holidays
[10 empty] | 27 | Working Days
[10 empty] | 4 | Number of Devs
[10 empty] | 80% | Load factor
[10 empty] | 345.6 | Available Dev Hours
[10 empty] | 12.8 | Daily Dev Hours