## Sheet1
General Project Information
|  | Project Name | City youth APP
|  | sprint time | 2week
|  | scrum master | Dina ahraf
|  | Stakeholders | any student want to join
|  | Expected Start Date | 2018-03-01
|  | Expected Completion Date | 2018-05-16
|  | product owner | City youth Organization
|  | Budget | 15000$
Planning | Name | Story | Priority | Status | Analysis | Responsible | Design | Responsible | Implementation | Responsible | Testing | Responsible | Start | End | Days
Sprint 1 | LoginPage |  | High | Complete | [8 empty] | 2018-03-01 | 2018-03-15 | 14
Feature 1 | Login | as a :user I want to:enter to website so that enter my email and passowrd | High | Complete | analysis what Login have | ahmed mansour | design Login | Dina | coding Login | ahmed masnour | testing the page | ahmed mansour | 2018-03-01 | 2018-03-08 | 7
task1 | table of the user regestration | as a :user I want to:enter to app so that: have email and password | High | Complete | analysis what the table have | mohamed montaser | create the relational tables of users | Ahmed mansour | connect the project to the table in data base | mohamed montaser | testing the table | ahmed mansour | 2018-03-01 | 2018-03-04 | 3
task 2 | encoding the passowrd | as a :user I want to:enter to app by my email and pass so no one can change my data | High | Complete | analysis what the code have | ahmed mansour | design in data base | Mohamed khaled | coding the part of encoding | ahmed masnour | testing the code | ahmed mansour | 2018-03-04 | 2018-03-08 | 4
Feature 2 | home page | as a :user I want:enter the app and show all the features | high | Complete | analysis how the home page would be | ester | design how the home page would be | Ester | no coding needed | ahmed mansour | testing that the home page work | ahmed mansour | 2018-03-08 | 2018-03-15 | 7
Sprint 2 | stuff page |  | High | In Progress | [8 empty] | 2018-03-15 | 2018-03-29 | 14
Feature 3 | stuff page | as a :user I want:enter to website so that: watch all employee and add new employee and do edit on the data | High | In Progress | analysis what Stuff page have | ahmed mansour | design stuff page | Dina | no coding needed | mohamed khaled | testing the page | mohamed montaser | 2018-03-15 | 2018-03-22 | 7
task 1 | knowing all the comen employee | as a :user I want:enter to courses so that: search on how employee | High | In Progress | analysis what the page shown | mohamed montaser | design the page design | Ester | no coding needed | mohamed khaled | testing the page | mohamed khaled | 2018-03-15 | 2018-03-18 | 3
task 2 | searching | as a :user I want:enter to page so that: search on spacific employee | High | In Progress | analysis the search seem | ahmed mansour | design the shape of search | ahmed mansour | coding search | ahmed mansour | testing the search work | ahmed mansour | 2018-03-18 | 2018-03-22 | 4
Feature 4 | admin preveliges | as a :user I want:enter to all app so that:edit on specific information | Medium | Not Started | analysis info admin | ahmed | design the admin pages | mohamed montaser | coding the code of seccurity | ahmed mansour | testing the page | ahmed mansour | 2018-03-22 | 2018-03-29 | 7
task 1 | knowing information | as a :user I want:enter to page so that:know each information about employee | Medium | Not Started | analysis the admin table and the role that have | ahmed mansour | design the admin name shape | Ester | coding the instructor Privileges | ahmed mansour | testing database | ahmed mansour | 2018-03-22 | 2018-03-26 | 4
task 2 | edit information | as a :user I want:enter to all pages so that:edit on a specific data | Medium | Not Started | design the navigation bar | ahmed mansour | design the shape of buttons | Ester | coding the part | ahmed mansour | testing the code | ahmed mansour | 2018-03-26 | 2018-03-29 | 3
Sprint 3 | student enrollment |  | Medium | Not Started | [8 empty] | 2018-03-29 | 2018-04-12 | 14
Feature 5 | enrollment | as a :user I want:enter to the student check so that: enroll the student | Medium | Not Started | analysis what the page contain | mohamed montaser | design the student page | Dina | no code needed | mohamed khaled | testing the code effciency | ahmed mansour | 2018-03-29 | 2018-04-05 | 7
task 1 | form | as a :user I want:enter student data so that: do submit | Medium | in progress | analysis what the form contain | mohamed khaled | design the form | Ester | coding the form and connecting with the data base | mohamed montaser | testing the form working | mohamed montaser | 2018-03-29 | 2018-04-02 | 4
task 2 | submit and send parameter | as a :user I want:click to submit so that:send the data to the next page | Medium | Not Started | analysis what the submit will do | ahmed mansour | design the button of submit | dina | coding button,connecting with data base | ahmed mansour | testing that it check on database | ahmed mansour | 2018-04-02 | 2018-04-05 | 3
Feature 6 | search on student | as a :user I want:make sure that the student found in the city so that: watch his data | Medium | in progress | analysis what the search button contain | ahmed mansour | design the button of the search | ahmed mansour | no code needed | mohamed khaled | testing the code effciency | Ester | 2018-04-05 | 2018-04-12 | 7
task 1 | connect with the student table | as a :user I want:enter the student name so that: click search | Medium | Not Started | analysis what the button contain | ahmed mansour | design the shape | ester | coding | yahia | testing the form working | yasser | 2018-04-05 | 2018-04-08 | 3
task 2 | submit | as a :user I want:click to the button so that: make account | Medium | Not Started | analysis what the submit will do | mohamed khaled | design the button of submit | ester | coding the button and connecting with database | mohamed montaser | send data to othe page | ahmed mansour | 2018-04-08 | 2018-04-12 | 4

## Sheet2
This sheet is to enable the drop-down lists
| High | Complete
| Medium | In Progress
| Low | Not Started